## Gantt
Gantt chart: AI Security for Critical Infrastructure (Guardrail Evaluation Test Bench and Beacon)
Guo Zi Qiang Robin, AAI4001 Capstone at LTA (CYAD). Capstone period 8 Oct 2026 to 31 Mar 2027. Weekly columns start on the date shown and run Thursday to Wednesday. See the Legend sheet.
Chart start date | 2026-10-08
[7 empty] | Oct 26 |  |  |  | Nov 26 |  |  |  | Dec 26 |  |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  | Apr 27
Task | Type | Start | End | Owner | Depends on | Deliverable | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-03 | 2026-12-10 | 2026-12-17 | 2026-12-24 | 2026-12-31 | 2027-01-07 | 2027-01-14 | 2027-01-21 | 2027-01-28 | 2027-02-04 | 2027-02-11 | 2027-02-18 | 2027-02-25 | 2027-03-04 | 2027-03-11 | 2027-03-18 | 2027-03-25 | 2027-04-01 | 2027-04-08
Academic milestones | Group
Form B submitted | Milestone | 2026-10-11 | 2026-10-11 | Robin | None | Form B_Guo_Zi_Qiang_Robin.docx | bar: 2026-10-08
Interim Report (Form E1) submitted | Milestone | 2026-12-06 | 2026-12-06 | Robin | Test bench evaluation report; Tier 1 results | Form E1 | bar: 2026-12-03
Interim Presentation | Milestone | 2027-01-31 | 2027-01-31 | Robin | Form E1; Beacon build progress | Interim Presentation | bar: 2027-01-28
Final Report (Form E2) submitted | Milestone | 2027-03-21 | 2027-03-21 | Robin | Deployed Beacon; test bench evaluation report | Form E2 | bar: 2027-03-18
Capstone period ends | Milestone | 2027-03-31 | 2027-03-31 | Robin | Form E2 | None (period boundary) | bar: 2027-03-25
Final Presentation (after the period) | Milestone | 2027-04-11 | 2027-04-11 | Robin | Form E2 | Final Presentation | bar: 2027-04-08
Write Interim Report (Form E1) | Task | 2026-11-23 | 2026-12-06 | Robin | Tier 1 results | Form E1 draft
Prepare Interim Presentation | Task | 2027-01-18 | 2027-01-31 | Robin | Beacon build under way | Slides and demo
Write Final Report (Form E2) | Task | 2027-03-01 | 2027-03-21 | Robin | Beacon deployed and monitored | Form E2 draft
Prepare Final Presentation | Task | 2027-03-22 | 2027-04-11 | Robin | Form E2 | Slides and demo
Workstream 1: Guardrail Evaluation Test Bench | Group
Complete comparative research (add Purple Llama and Litmus) | Task | 2026-10-08 | 2026-10-31 | Robin | None | Updated product research table
Build minimal reusable evaluation harness | Task | 2026-10-12 | 2026-11-08 | Robin | Comparative research | Evaluation harness (code)
Prepare labelled test inputs (public or synthetic only) | Task | 2026-10-26 | 2026-11-08 | Robin | Comparative research | Labelled test set
Document Tier 2 items under investigation, with reasons | Task | 2026-11-02 | 2026-11-30 | Robin | Comparative research | Tier 2 reasons note
Run Tier 1 evaluation (harmful-content and jailbreak checks) | Task | 2026-11-09 | 2026-11-27 | Robin | Harness; labelled test inputs | Raw results dataset
Analyse results and compare guardrails | Task | 2026-11-16 | 2026-12-01 | Robin | Evaluation runs | Comparison tables
Tier 1 evaluation results ready | Milestone | 2026-12-01 | 2026-12-01 | Robin | Evaluation runs | Results dataset | bar: 2026-11-26
Write test bench evaluation report | Task | 2026-12-01 | 2026-12-06 | Robin | Tier 1 results | Test bench evaluation report
Tidy harness, dataset and documentation | Task | 2026-12-07 | 2026-12-18 | Robin | Test bench evaluation report | Documented code and dataset
Workstream 2: Beacon | Group
Beacon design continues (low intensity) | Task | 2026-10-08 | 2026-11-30 | Robin | None | Design notes
Build collection (sources, page reading, storage) | Task | 2026-12-01 | 2026-12-20 | Robin | Beacon design | Daily collection run
Build filtering (on-topic check and labelling) | Task | 2026-12-14 | 2027-01-03 | Robin | Collection | Filtered, labelled items
Build merging of duplicate reports | Task | 2026-12-28 | 2027-01-17 | Robin | Filtering | Grouped developments
Build significance rating | Task | 2027-01-04 | 2027-01-24 | Robin | Merging | Rated developments
Build web Briefing and Telegram digest | Task | 2027-01-11 | 2027-01-29 | Robin | Rating | Web Briefing; Telegram digest
Initial mapping to SSP controls and MITRE ATT&CK / ATLAS | Task | 2027-01-18 | 2027-01-31 | Robin | Rating | Mapped developments with evidence
Integrate and deploy | Task | 2027-01-25 | 2027-02-01 | Robin | Briefing, digest and mapping built | Deployed Beacon
Beacon deployed | Milestone | 2027-02-01 | 2027-02-01 | Robin | Integration | Live service | bar: 2027-01-28
CI/CD pipeline | Task | 2027-02-01 | 2027-02-28 | Robin | Deployed Beacon | Automated build and release
Monitoring and fixes | Task | 2027-02-01 | 2027-02-28 | Robin | Deployed Beacon | Monitoring and incident notes
Trend detection (stretch goal) | Task | 2027-02-15 | 2027-03-15 | Robin | Stable pipeline | Trend view, if time allows
Buffer and iteration | Task | 2027-03-01 | 2027-03-31 | Robin | Monitoring results | Fixes; source code and documentation

## Legend
Legend
Blue bar | Task: shaded in every week the task is active (formula-driven from Start and End)
Amber cell with a diamond | Milestone: a fixed date set by SIT or by the plan
Grey bar | Stretch goal: done only if earlier stages are stable
Light-blue row | Group heading
How to edit: change Start or End dates (blue text, columns C and D) and the bars redraw. Change the chart start date in Gantt!B3 to shift the weekly columns.
Weekly columns: 27 weeks from Thu 8 Oct 2026; the last column (week of 8 Apr 2027) contains the Final Presentation on 11 Apr 2027.
Capstone period: 8 Oct 2026 to 31 Mar 2027. The Final Presentation on 11 Apr 2027 falls after the period.
Phasing: Workstream 1 is heavier from Oct to early Dec; Workstream 2 design continues at low intensity, then the build runs Dec to Jan.
Assumptions: single owner (the student) for all rows; sub-task dates inside each phase are planning estimates; Trend detection is a stretch goal; Tier 2 comparisons are under investigation and not scheduled for evaluation.
Example of a row: 'Run Tier 1 evaluation' ¦ Task ¦ 9 Nov 2026 ¦ 27 Nov 2026 ¦ Robin ¦ Harness; labelled test inputs ¦ Raw results dataset.